## Sheet1
MegaMart Compliance Gap Assessment
# | Control ID | Control Area | Current State (As-Is) | Evidence Reviewed | Gap Identified | Expected State | Risk Level (H/M/L) | Impact | Recommendation (To-Be) | Responsible Owner | Priority (1/2/3) | Target Date | Status
1 | C-01 | Data Retention | Data lake holds customer data for 6 years (no retention policy) | Retention reports, policy docs | No formal retention policy; data kept longer than necessary | GDPR Art.5: data minimization & storage limitation; ISO 27001 A.8.3: define retention periods & secure deletion; CIS 3.4: Enforce Data Retention | High | High | Implement data retention policy; enforce once in three years, deletion of old data | IT Team | 2 | 30 days | In progress
2 | C-02 | Device Security | Warehouse handheld scanners run Android 7 (no patches) | Device inventory, patch logs | Outdated OS; unpatched vulnerabilities | ISO 27001 A.12.6 & CIS 7.3: Timely OS patching; OWASP A06: Vulnerable and Outdated Components | High | High | Upgrade devices/OS; implement patch management and vulnerability scanning | Warehouse IT Team | 1 | 60 days | In progress
3 | C-03 | Server Security | Website uses Cloudflare, but origin servers unpatched Ubuntu 18.04 | Vulnerability scans, firewall configurations | EOL (End Of Life) OS; unpatched servers | OWASP A06: Vulnerable and Outdated Components; ISO 27001 A.12.6 & CIS 4: server hardening & patching; GDPR Art.32: secure processing | High | High | Upgrade OS; apply patches; implement network segmentation, firewall, and secure configs; Cloudflare noted as mitigation | Web Admin/ IT Team | 1 | 45 days | In progress
4 | C-04 | Web Application Security | Bot protection disabled to reduce CDN costs | CDN configuration screenshots | No protection against automated attacks | OWASP A05: Security Misconfiguration; ISO 27001 A.12.4: logging & monitoring | Medium | Medium | Enable bot protection; implement WAF and monitoring | Web Admin/ IT Team | 2 | 30 days | Planned
5 | C-05 | File Upload Security | 3rd-party sellers upload product files (no file scanning) | Upload logs, antivirus reports | Malicious files could be uploaded and executed | OWASP File Upload Security Cheat Sheet; ISO 27001 A.12.2: malware protection; CIS 10: Malware Defense | High | High | Implement file scanning/antivirus; restrict file types; sandbox uploads | Web Admin/ IT Team | 1 | 30 days | In progress
6 | C-06 | Payment Data Security | Customer support accesses full card numbers (no truncation) | Access logs, PCI DSS reports | Full PAN visible; sensitive data not masked | PCI DSS Req.3: mask PAN; ISO 27001 A.9: access control; OWASP A02: Cryptographic Failures; GDPR Art.25: data protection by design | High | High | Implement card truncation/masking; restrict access; audit logs | Head of Customer Support / IT Team | 1 | 30 days | In progress
7 | C-07 | Data Privacy | Marketing team uses public Trello boards for campaign planning & customer data | Trello board exports | Sensitive data publicly exposed | ISO 27001 A.8/A.9: access control & classification; GDPR Art.32: protect personal data | High | High | Move data to private/internal tools; implement access controls and staff training | Marketing Head | 1 | 30 days | In progress
8 | C-08 | Vendor Security | Vendor delivering SMS OTPs not under any security agreement | Vendor contracts, SLA (Service Legal Agreements) docs | No contractual security requirements | ISO 27001 A.15 / SOC2: security clauses in vendor contracts; GDPR Art.28: data processing agreement required | Medium | Medium | Sign security agreement; define encryption and data handling SLAs | Vendor Management/ IT Team | 2 | 60 days | Planned
9 | C-09 | Logging & Monitoring | Load balancer logs stored but never reviewed | LB logs, SIEM configurations | Logs not actively monitored | ISO 27001 A.12.4: logging & monitoring; OWASP A09: Security Logging & Monitoring | Medium | Medium | Implement log monitoring, alerting, regular review | Network/ IT Team | 3 | 20 days | Planned
10 | C-10 | Backup Security | Backups stored on the same AWS account (no separation of duties) | Backup configuration, IAM (Identity and Access Management) policies | No separation of duties; risk of simultaneous loss | ISO 27001 A.12.3 / NIST CP-9: backup isolation; CIS 11: controlled recovery; GDPR Art.32: protect backup integrity | High | High | Store backups in separate accounts/regions; enforce access restrictions; test DR (Disaster Recovery ) plan | IT Team | 2 | 45 days | In progress