## Sheet1
Risk Analysis for E-Commerce Startup
Risk ID | Asset / Process | Threat | Vulnerability | Risk Description | Impact (H/M/L) | Likelihood (H/M/L) | Inherent Risk | Existing Controls | Control Effectiveness (Strong/Medium/Weak) | Residual Risk | Risk Owner | Recommendation | Target Date | Status
R1 | Customer Data (PII) | Unauthorized access / Data breach | Weak access controls, Shared credentials | Sensitive customer PII may be accessed by unauthorized personnel through inadequate access management | High | Medium | High | Password policy exists; MFA only enabled for admins | Medium | Medium | IT Manager | Enforce MFA for all users, implement RBAC, stop credential sharing | 30 days | In progress
R2 | Customer Data (PII) | Insider misuse | Employee mishandling of data | Employees may accidentally or intentionally misuse customer data | Medium | Medium | Medium | NDA Agreements (Non-Disclosure Agreements) | Medium | Medium | HR/ IT Manager | Monitor data access, logging, regular audits. | 30 days | In progress
R3 | Cloud Server | Server downtime | No redundancy (backups), outdated software | Operations may be disrupted if cloud server fails | High | Medium | High | Cloud provider SLA (Service Level Agreement), automatic backups | Medium | Medium | IT Manager | Implement backup servers in multiple regions and keep software up to date | 30 days | Planned
R4 | Accounts (Employee & Customer) | Weak passwords | Use of weak or easily guessable passwords | Weak passwords increase the likelihood of unauthorized access to systems and accounts | High | High | High | Password complexity policy for admins only | Low | High | IT Manager | Enforce strong password policies for all accounts, implement MFA | 20 days | In progress
R5 | Employees | Phishing / Social engineering | Lack of cybersecurity training | Employees may fall victim to phishing emails leading to data compromise | Medium | Medium | Medium | Basic email filters, phishing email detectors | Low | Medium | HR/ IT Manager | Conduct cybersecurity training, phishing simulations | 60 days | Planned
R6 | Payment Gateway | Fraudulent transactions | Weak authentication, unsecured APIs | Risk of financial fraud or unauthorized payments | High | High | Medium | SSL/TLS for payment API | Medium | Medium | Finance/ IT Manager | Stronger API authentication, transaction monitoring | 30 days | In progress
R7 | Website / Application | DDoS attack | Limited bandwidth, no mitigation strategy | Website may become unavailable due to a DDoS attack | Medium | Medium | Medium | Basic firewall | Medium | Medium | IT Manager | Implement DDoS protection service, load balancers | 30 days | In progress
R8 | Employee Devices | Malware / Ransomware | Personal devices used for work, outdated antivirus | Devices may be infected leading to data loss or compromise | High | Medium | High | Antivirus installed | Medium | Medium | IT Manager | Enforce endpoint security, regular updates, restrict personal devices | 30 days | Planned
R9 | Physical Office Premises | Theft / Unauthorized access | No access control system | Physical assets or devices may be stolen or tampered with | Medium | Low | Medium | Basic locks | Low | Low | Office Manager | Install access control, CCTV cameras | 10 days | In progress
R10 | Company Reputation | Negative publicity / Social media backlash | Poor incident response | Reputation may be damaged due to mishandled incidents | High | Medium | High | PR (Public Relations) guidelines | Medium | Medium | PR Team | Develop crisis management & communication plan | 60 days | Planned
R11 | Business Processes | Human error | Manual processes, lack of verification | Errors in order processing or data entry may occur | Medium | Medium | Medium | Basic SOPs (Standard Operating Procedures) | Medium | Medium | Operations Manager | Automate workflows, implement double-check system | 30 days | In progress
R12 | Regulatory Compliance | Non-compliance fines | Lack of awareness of data protection / PCI DSS | Company may face legal penalties | High | Low | Medium | Basic compliance awareness | Medium | Medium | Compliance Officer | Conduct regular audits, employee training | 90 days | Planned